## Sheet1
Category |  | Description of the problem | Solutions found / best practice
Financial aspects | Payments to participants | 1. Allocation of grants to participants (IN + OUT) > Administratively demanding for Programme HEIs 2. Pre-financing payments VS direct provision > Students from Partner HEIs often need to cover costs before receiving financial support (e.g. plane tickets), de facto limiting ICM to elites > Fear of Programme HEIs to pre-finance in case participant does not show up > Some Programme HEIs propose only direct provision of Individual Support (IS) & Travel Support (TS) to staff from Partner HEIs 3. Problems with bank accounts and transfers > No possibility to open bank account for stays below 6 months (e.g. Norway) or if no permanent address in country (e.g. Italy or Belgium) > In some countries (e.g. Estonia) opening bank accounts for non-residents is expensive (150-200€). Once residence permit is obtained accounts are free, but permits sometimes take several months. > Bank transfer costs > unclear who should pay for them > Lengthy transfers > some students receive their grants several weeks after arrival > Short duration of staff mobility > can lead to payment after end of mobility > Citizens of some countries do not have personal bank accounts > not possible to send pre-financing payment 4. Zero-grant participants & zero-grant extensions > Some students not informed that will not receive IS or TS, discovering it upon arrival > Zero-grant extensions unofficially agreed on with participants before start of mobility, de facto reducing grant amount | Programme Guide, p. 36: "For mobility between Programme and Partner Countries, only HEIs from Programme Countries can apply and administer the payments for inbound and outbout participants" 1. Allocation of grants to participants (IN + OUT) > Split of tasks and responsibilities should be reflected in split of OS 2. Pre-financing payments VS direct provision Participant Grant Agreement (GA) --> Article 4 of participant GA modified by EC, allowing for more flexibility in payments > For STAFF mobility - Three options in GA: 1) Staff receives IS & TS in EUR 2) HEI provides IS & TS in form of direct provision 3) Staff receives part of financial support in EUR and part in direction provision > For STUDENT mobility: "direct provision" applies only to travel support services (> should be used to widen participation, in particular for disadvantaged backgrounds) > GA template can be modified by NA or Programme HEI, leaving freedom to define payment provisions, deadlines and amounts. Please discuss preferable options with your partners 3. Problems with opening bank accounts and transfers > Participant GA indicates that financial support should be paid by bank transfer to bank account indicated on page 1 > GA foresees cases where bank account holder is different than participant > Very exceptionally, Programme HEI can use other payment methods for first months If student declares on honour that unable to provide valid bank account in any country, alternative payment method can be considered > GA provisions should clearly state applicable payment method > Must be fully documented, including explicit acknowledgement of receipt of amount by participant. > Bank transfer costs: Programme HEI not allowed making cash payments to participants only to avoid bank transfer costs. HEI could use OS to cover transfer costs > Delays due to bank transfers: GA with participant refers to when participant should receive payment. If HEI expects delays, participants should be informed accordingly. > If no personal bank account in Partner Country: direct provision + alternative payment methods Examples in MS: bank payment card when they arrive (e.g. BE); find banks that accept to provide such services to non-citizens (e.g. IT); payments by bank draft (e.g. IE); cash payments (e.g. EE); cover costs for incoming students upon arrival (e.g. FI); transfer money to Partner HEI (e.g. DK) 4. Zero-grant participants or zero-grant extensions > Students supposed to sign GA with beneficiary before start of mobility > If not possible, students should at least receive completed GA template, including info on financial support > Student should always be made aware on availability or not of IS&TS before applying for mobility (including extension). In many cases, students accept going as zero-grants. > If inconsistency between GA and funds available upon arrival, other funds should be used to provide IS & TS > Zero-grant extensions only possible after start date of mobility period. Extensions = exception (e.g. exam date after mobility end date) Best practice: Latvia: Agreement between HEI & bank --> students can submit their applications for opening an account to bank before their arrival --> Before start of the semester, HEI sends an official letter informing bank of names --> Bank is aware that opening of accounts should be free of charge and fast --> speeds up the process considerably
| Grant amount | 1. Insufficient financial support --> IS too low compared to costs of living in certain countries (e.g. NO) --> Some countries (e.g. NL) require additional 100 €/month as minimum funding for visa requirements + 300 € for residence permit + 400 € for accommodation etc. 2. Variation in grant amount after amendments --> incoming and outgoing participants don't receive same amounts. In case of changes to GA between NA-HEI, overall grant is recalculated --> Sometimes small amount is missing and it is not possible to approve a higher number of participants/duration of mobility | 1. Insufficient financial support Programme Guide, p. 46: HEIs can top up EU grant with own funds/national funds --> Participant GA (art.3) includes possibility to provide financial support other than Erasmus+ EU funds --> E.g. NO HEIs add funding from own budgets to ensure ICM students receive same amount as other incoming students funded by other (national) programmes --> Please continue sharing this kind of data: issues linked to grant rates will be taken into account in the framework of the on-going study to review simplified grants and info is needed 2. Variation in grant amount after amendments --> Grant will go up and down during project life cycle. Important that at final report stage, it does not exceed grant awarded --> Possible solution: organise shorter mobilites --> EC looking at ways to limit amendments
| Grant taxation | 1. Problematic tax legislation in some countries --> Estonia: income tax needs to be deducted from staff grants --> Norway: tax authorities can in theory require taxes from incoming PhD candidates and staff --> Slovenia: Grants are regarded as additional funds and taxed --> Finland: Grants of incoming PhDs exceeding 6 months are taxable --> Poland: Taxation rules applied to citizens from third countries differently understood by some HEIs' financial offices | Legal basis: Regulation of the EP and the Council establishing Erasmus+: “Member States should also be encouraged to exempt those grants from any taxes and social levies.” --> HEIs, NAs and NEOs need to dialogue with tax authorities and relevant Ministries (e.g. in Poland new law on tax exemption is expected by the end of the year) Best practice examples: --> Estonia: Some HEIs deduct taxes from OS --> Finland: Organise shorter mobilities --> Slovenia: Direct provision (e.g. pay accomodation and travel) --> Poland: Ministry of Science and Higher Education and Ministry of Finance working on solution to exempt third country incoming students and staff from taxation
| Budget Absorption | 1. Difficulties to use all the budget allocated Low absorption due to problems encountered during implementation of projects --> Some IIAs do not enter into force due to misunderstandings (e.g. related to split of OS) --> Some partners want to add clauses to IIA after GA signature --> Delays and cancellations --> Management-heavy and inflexibel amendment procedure | 1. Difficulties to use all the budget allocated --> Inform your NA/NEO --> Adjust plans over lifecycle of project, e.g. allocate funding to most active partner institutions in the framework of redistribution of funds --> Must-read document: Guide on Amendments (June 2016) > EC currently reviewing it to make it more flexible (2016 & 2017) projects
Participant-related problems | Selection of participants | 1. Short timeframe between award notification and deadline for selection of participants --> Due to short timeframe, HEIs in Partner countries sometimes fail to nominate participants and produce requested documentation in time 2. Allocation of mobility places per Partner Country and not per HEI --> Unclear how many places available per HEI, how selection is made, what role of sending institution is etc. --> Mostly happening in former EM Action 2 Programme HEIs, which were following such application/selection procedures 3. Selection decision at Programme HEI VS Partner HEI --> In many cases, whole selection process remains with Programme HEI (participants apply directly, bypassing Partner HEI) --> Some Programme HEIs do not provide explanations on final decision --> Discourages students to apply, as selection criteria not clear 4. Different procedures/deadlines for nomination and selection of participants --> requires a lot of preparation and administrative work 5. Lack of information on ICM opportunities and benefits --> In many cases, individuals do not know about opportunities available --> In particular lack of knowledge on benefits of staff mobility 6. Lack of interest, lack of suitable candidates --> fear of going to a completely different culture; resignation at the last minute; different length of the semester etc. 7. Weak English knowledge of applicants | 1. Short timeframe between award notification and deadline for selection of participants --> HEIs need to optimise and adjust their internal institutional procedures --> More in-depth analysis before decision of cooperation with given partner (e.g. discuss HEI's expectations, internal procedures etc.) --> Many HEIs accept student applications after deadline for submission. However, this leads to students arriving late, missing beginning of studies and being subject to additional workload 2. Allocation of mobility places per Partner Country and not per HEI --> Number of available mobilities per HEI needs to be communicated clearly to all partners 3. Selection decision at Programme HEI VS Partner HEI --> Different possibilities for selection: a. Sending institution selects outgoing participants b. Preselection in Partner HEI, final selection in Programme HEI c. Whole selection process in Programme HEI --> Partners need to mutually agree on chosen selection procedures, number of participants sent/received etc. --> E.g. Selection criteria in written approved by both university authorities --> In all cases: Selection needs to be fair and transparent. Individual appeals are possible (to HEI, NA and ultimately EC) --> In case of subsisting problems, HEI should contact NEO or alert NA 4. Different procedures/deadlines for nomination and selection of participants Not possible to harmonise all procedures --> HEIs need to communicate well with partners --> Workshops and trainings can be organised at national level to try and harmonise procedures --> Overall improvements since last year (action better known) 5. Lack of information / lack of interest --> Establish information-delivery-mechanisms (e.g. newsletter, website, billboard) --> develop strategy in HEI to recognise staff mobility (e.g. workshops/lectures to share outcomes & provisions on career promotion) --> Increase promotion (e.g. ask previous mobile participants to share experience) + make use of organisations such as ESN, ESAA etc. 7. Weak English knowledge of applicants --> Use OS funds to organise additional English courses before or after departure
| Course catalogue | 1. Differences in study programmes and curriculum descriptions in Partner and Programme HEIs --> students face difficulties in choosing courses --> sometimes, length of the study programmes do not correspond to mobility duration (e.g. Belarus: max duration = 3 months, however, a semester usually lasts 4 months) 2. IIAs signed by HEIs, not faculties --> IIAs are often multidisciplinary, with no details on study programmes --> Problem: nomination of students depends on list of courses taught abroad + recognised upon return 3. Late update of course catalogues --> Course catalogue updated very late in the process (after nomination/application deadlines) 4. Unexpected changes at receiving HEI --> Even if course catalogue is updated, many announced courses never happen, some are impossible to register for (e.g. already full at time of selection), rejections by course professors etc. --> Difficult to anticipate in advance, as such information rarely appears on receiving HEIs website 5. Courses approved at application stage and courses finally realised do not correspond --> E.g. LA signed before update of course catalogue --> Especially problematic in non-anglophone countries with limited English-taught programmes 5. Amendment of Learning Agreement --> Due to specific laws (e.g. Belarus) or procedures, difficult to change LA after start of mobility --> Students cannot follow courses they are interested in if not included in LA before mobility | Must-read: Guidelines to Learning Agreement --> Updated course catalogue = prerequisite --> Available courses need to be discussed at application/nomination stage --> HEI management/professors responsible for recognition need to be flexible and look for compromise --> Best practice: Availability of full course descriptions within study programmes with clearly defined learning outcomes provided by both – Programme and Partner HEIs --> Report on recognition send to students after end of mobility to find out about problems
| Insurance, visa and travel support | 1. Unexpected visa costs --> UA example: Students had problems with getting National D-type visas in Consulates (e.g. Romania, Bulgaria, Czech Republic), where they were asked to pay a fee (600 Euro) --> FI example: Additional costs for residence permits for mobilities longer than 3 months 2. Visa rejections (e.g. UK, NO) 3. Visa duration does not correspond to mobility duration (NACO) 4. Lengthy and costly visa procedures --> Participants might have to travel to and stay in another country to submit application 5. Insufficient Travel Support 6. No additional funds for insurance costs | General comment: EC letter to permanent representations of EU MS (Jan 2015 + Jan 2016), warning of increased mobilities due to E+ 1. Unexpected visa costs --> Best practice: Use OS to cover visa costs --> UA example: Students got Schengen C-type visas (at their own risks) 2. Visa rejections --> Involve Ministries (of Education, Foreign Affairs) --> Norway example: HEI wrote note to Ministry of Education informing about obligations to minimize potential barriers to mobility 3. Visa duration does not correspond to mobility duration --> HEIs should be flexible. In MT+, the minimum duration to be encoded is 58 days. Max: 360 days. 4. Lengthy and costly visa procedures --> Use OS for additional costs related to visa application process 5. Insufficient Travel Support --> Travel support = Top-up unit cost. In some case will be more, in some cases less. Up to HEI to see if it buys the tickets in kind to compensate the price differences --> Use OS or own funds to complement 6. No additional funds for insurance costs --> Some HEI agreed with partners that insurance for students will be covered from OS funds --> Others are asking participants to cover the insurance costs themselves. General advise: use international enterprises to have suitable coverage.
| Recognition | 1. Problems with recognition of learning outcomes by sending HEIs 2. Curricula of Programme HEI and Partner HEIs do not coincide 3. No ECTS in some Partner Countries 4. Recognition for PhD candidates/staff --> Some countries do not use ECTS for doctoral candidates, but number of hours (e.g. in Latvian HEIs there is no such system for incoming PhD candidates therefore it is difficult to control and prove how many hours a doctoral candidate spent for his studies) --> No ECTS for staff | 1. Problems with recognition of learning outcomes by sending HEIs --> Some HEIs implement compulsory recognition of ICM outcomes, forcing responsible choice of subjects by students and approval by administration before signing LAs 2. Curricula of Programme HEI and Partner HEIs do not coincide --> Be flexible --> Moldova example: HEIs add clause to IIA allowing students to pick courses from other study years (within same study level (BA or MA)) 3. No ECTS in some Partner Countries --> Bologna countries should all use ECTS --> Set up Capacity-Building projects to help Partner HEIs implement ECTS General comment: All Eastern Partnership Countries are Bologna members and should therefore use ECTS credits. Report on recognition will show us where problems remain.
| Complaints | 1. Complaint mechanisms --> Many students keep silent on problematic or unfair selection/implementation (out of fear of repercussions or lack of knowledge) --> Difficult to ensure fair and transparent selection (merit-based) + recognition | --> Students can appeal to HEI, NA and ultimately EC --> Participant report and report on recognition provide NAs and EC with direct feedback
Partnership-related problems | Split of tasks & responsibility (Inter-Institutional Agreement) | 1. Amendments after GA & IIA signature --> different HEIs ask for different changes (e.g. mobility levels, mobility duration, flow direction etc.) --> Unclear for Partner HEIs which changes are possible under which conditions (formal amendment or not?) 2. Partner Country HEIs not consulted on IIA --> In some cases, split of tasks and responsibilities not discussed with partners. IIA filled by Programme HEI and sent for formal signing without discussion on content. 3. Late signature of IIAs --> IIAs often signed right before start of ICM mobilities, leaving little time for discussion of implementation issues or participant selection 4. Lack of knowledge in Partner HEIs 5. No International Relations Offices in some Partner Countries --> difficult communication + uneven split of tasks and responsibilities | 1. Amendments after GA & IIA signature Must-read document: 2016 Guide on Amendments --> Ongoing internal discussions for easing amendment process (2016 & 2017 projects) --> formal amendemnts only if change of Partner HEI, change of project duration, special needs and redistribution of funds. Probably some flexibility to change flows direction without amendment (if more than 20% of budget affected > amendment) --> Partner Country HEIs are welcome to read the guidelines existing for beneficiaries, the June 2016 version will be reviewed once a decision is taken on the above discussion. 2. Partner Country HEIs not consulted on IIA --> ICM projects are partnerships. Even if Partner HEIs do not sign GA, they should be involved in drafting of IIA before start of mobilities --> IIA cannot be effective until they give their approval and sign it. Their input is also essential to prepare good quality applications. --> Also possible to solve misunderstandings and bottlenecks on ad hoc basis once practical implementation starts 3. Late signature of IIAs --> Grant award notification in June --> 2 months before first mobilities start --> IIA should be discussed during application phase already (before February), even if finalised only over the summer 4. Lack of knowledge in Partner HEIs --> Must-read document: "Quick Reference Guide for Partner Country HEIs" --> Programme HEIs need to be active and distribute useful documents (e.g. FAQs, guidelines etc.) to inform and prepare partners --> NEOs = resource persons in Partner Countries 5.No International Relations Office in some Partner Countries --> Prepare Partner HEI in best possible way, e.g. organise staff training (supported by STT-grants) on administration of mobilities --> Partner HEIs should apply for Capacity Buidling in Higher Education projects to set up Int. Rel. Offices General comment: most common tasks at Partner HEIs = selection process, administrative support for mobilities, promotion
| Organisational Support | 1. Split of OS between Partner and Programme Country HEIs Sometimes uneven split, sometimes no split at all --> Many Programme HEIs not willing to share OS with Partner HEIs --> Some Partner HEIs too demanding --> Some Programme HEIs unilaterally decide to use OS to fund additional mobilities (i.e. to cover travel costs when initial mobility period is shortened), rather than sharing it with partner or covering visa/insurance/bank transfer costs | Legal basis: Programme Guide, p.45 "OS grant will be shared by the partners concerned on a mutually acceptable basis decided upon by the participating institutions" --> Although GA is signed between Programme Country HEI and NA, ICM projects are partnerships, and partners should be treated as equals. The split of OS should be based on the distribution of responsibilities and tasks. Transparent communication is encouraged, as well as feedback to NEOs and NAs in case of problems. --> OS (50%) can be used for additional mobilties only if there is clear leftover and no impact on the quality of the mobilities (PG p. 45) --> In case of leftover, OS can be used for language training, to cover IS of longer mobilities or IS/TS of additional mobilities, to cover visa or insurance-related costs etc. It is important to: 1. clearly indicate in the IIA the distribution of OS between Partner and Programme HEIs 2. Communicate well 3. Make sure that OS is not needed to cover other expenses (visa, insurance, travel, bank transfer etc.) before allocating it to additional mobilities
| Monitoring, communication & reporting | 1. Lack of or slow communication between partners 2. Lack of information on Erasmus+ programme at Partner HEI 3. Lack of instructions from Programme HEI (on reporting requirements / templates used) 4. Lack of capacity and experience with project management tasks/coordination of mobility projects at Partner HEI 5. Difference between Programme/Partner Countries (e.g holidays, time difference, semesters etc.) | --> Must-read: "Quick Reference Guide for Partner Country HEIs" --> Establish expectations around working practice (email response times, regularity of meetings etc.) --> Spend necessary amount of time + efforts re-sending e-mails and reminders to partners to solve issues (better to ask for explanation/additional information than not react at all) --> Build capacity and share know-how: e.g. staff training visits to Programme HEI by Partner HEI staff, preparatory visits, monitoring visits etc. General comment: Mobility Tool+ needs to be updated on a monthly basis. MT+ access is restricted to Programme HEI. HOWEVER, Programme HEI can give view access to contact persons from Partner HEI.
Other | Country specific challenges | E.g. Border control in Gaza, emergency state Turkey, security challenges in eastern Ukraine, student protests in Chile etc. --> State of uncertainty discouraging students and staff from going abroad | Be flexible. Final decision lies with individual participant. Ensure ongoing contacts between partners to enable modification to the original mobility scheme
| Sustainability | No guarantee that partnership will be reselected for funding | Establish enduring cooperation funding schemes that survive the possible short time span of Erasmus+ funding
ICM | International Credit Mobility
IS | Individual Support
TS | Travel Support
GA | Grant Agreement
OS | Organisational Support
HEI | Higher Education Institution
PG | Programme Guide
NA | National Agency
NEO | National Erasums+ Office
IIA | Interinstitutional Agreement